## Projects
ID | Project name | Dept | Project owner | Support | Status | Flag | Progress | Start date | Due date | Done date | Effort (days) | Budget (USD) | Notes
P-001 | Website redesign | Marketing | Layla Khan |  | In progress |  | 60% | 2026-03-01 | 2026-03-15 |  | 15 | 20000
P-002 | Brand guidelines | Marketing | Layla Khan |  | In progress | Review | 60% | 2026-03-02 | 2026-04-30 |  | 12 | 20000 | Waiting for agency
P-003 | CRM migration | IT | Bilal Aziz |  | Blocked |  | 45% | 2026-02-10 | 2026-05-20 |  | 40 | 22700
P-004 | Q2 hiring plan | HR | Sara Nasser | Bilal Aziz | Done |  | 100% | 2026-01-05 | 2026-02-28 | 2026-02-26 | 20 | 15000
P-005 | Warehouse automation | Operations | Maya Haddad |  | In progress |  | 95% | 2026-02-01 | 2026-11-30 |  | 90 | 320000
P-006 | Vendor onboarding portal | IT | Layla Khan |  | At risk |  | 10% | 2026-01-01 | 2026-02-20 |  | 30 | 40000
P-007 | Annual report design | Marketing | Omar Saleh |  | In progress |  | 30% | 2026-03-01 | 2026-12-30 |  | 25 | 9000
P-008 | Payroll system upgrade | HR | Sara Nasser |  | In progress |  | 40% | 2026-01-15 | 2026-02-10 |  | 35 | 60000
P-009 | Office move | Operations | Bilal Aziz |  | Not started |  | 0% |  |  |  | 10 | 500 | Needs a date
P-010 | Customer survey | Marketing | Maya Haddad |  | Done |  | 100% | 2026-02-01 | 2026-03-01 | 2026-03-01 | 8 | 7000

## Lists
Status | Dept | Owner | Flag
Not started | Marketing | Layla Khan | Review
In progress | IT | Bilal Aziz
At risk | HR | Sara Nasser
Blocked | Operations | Maya Haddad
Done | Finance | Omar Saleh

## Read me
How this tracker works
One row is one project. No empty rows, no totals typed by hand, no merged cells.
Every row has an ID. It never changes, even when the name does.
Status, Dept, Owner and Flag are picked from lists. Edit the lists on the "Lists" sheet.
Dates are real dates (2026-09-30) or empty. Start, Due and Done are three separate columns.
Late is never typed. A row turns red by itself when its due date has passed and its status is not Done.
Numbers are numbers. The unit lives in the header: Effort (days), Budget (USD).
Need to mark a row? Use the Flag column, not a cell color.
What each status means
Not started: no work yet.
In progress: work is moving and the due date still holds.
At risk: the due date is in danger unless something changes. Say what in Notes.
Blocked: work cannot continue until someone else acts. Say who in Notes.
Done: delivered and accepted. Fill the Done date.
The ten rows on the Projects sheet are examples with invented names. Delete them and add your own.
Want to see it as a dashboard? Load this file in Dashboard Studio: darwishqannan.com/studio
Made by Darwish Qannan. Free to use and share.